## Sheet1
DBANK DEMO Group Number - 02 Team Lead - Bondili Shriya singh thakur(Emp - 2577118)

## Status Tracking
Project Status Check Report Group 2
| SI.NO. | Employee ID | Name | Domain | Module | 06-Dec-23 | 07-Dec-23 | 08-Dec-23 | 09-Dec-23 | 11-Dec-23 | 12-Dec-23 | 13-Dec-23 | 14-Dec-23
| 1 | 2577118 | Bondili Shriya singh thakur | Testing | JIRA | Exlporing the JIRA | Test Management in JIRA | Test Management in JIRA | Test Management in JIRA | Test Management in JIRA | Test Management in JIRA | Test Management in JIRA - raising defects | Creating PowerPoint Presentation
| 2 | 2575882 | Ashutosh Jha | Testing | Sign up | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation
| 3 | 2575839 | Vaibhav Kumar | Testing | Sign in | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation
| 4 | 2576444 | Kasani Aparna | Testing | Deposit into Account | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation
| 5 | 2576331 | Pruthvishree S k | Testing | Withdraw from Account | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation
| 6 | 2576094 | M Naveen Kumar | Testing | Transfer Between Accounts | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation
| 7 | 2576992 | Mukul Parmar | Testing | Direct Payment to VISA | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation
| 8 | 2575542 | Bandaru Sandhya Rani | Testing | Search by TRN no on View Checking Accounts | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation
| 9 | 2575699 | Rishikesh X | Testing | Search by TRN no on View Saving Accounts | Manual Testing -Test Scenario | Page Object designing | Creating Test class with validations | Creating Cucumber feature | Implementing step definitions | Adding Listeners, log4j2, extent reports, retryanalyzer | Integrating the project | Creating PowerPoint Presentation

## Status Meeting
Status Meeting Group - Team 2
| Meeting Date | Time | Progress Check | Time2 | Problem Solving | Time3 | Collabration
| 2023-12-06 | 10:00 | a | 14:00 | a | 18:00 | a
| 2023-12-07 | 10.00AM | a | 2.00PM | a | 6.00PM | a
| 2023-12-08 | 10.00AM | a | 2.00PM | a | 6.00PM | a
| 2023-12-09 | 10.00AM | a | 2.00PM | a | 6.00PM | a
| 2023-12-11 | 10.00AM | a | 2.00PM | a | 6.00PM | a
| 2023-12-12 | 10.00AM | a | 2.00PM | a | 6.00PM | a
| 2023-12-13 | 10.00AM | a | 2.00PM | a | 6.00PM | a
| 2023-12-14 | 10.00AM | a | 2.00PM | a | 6.00PM | a